Plan: Troop 9 Philmont Trek--2011

Goal: Develop Confidence for the Philmont Trek

How: Through practice and preparation.

Preparation: By attention to detail.

- Meet with boys and parents to discuss equipment needs and training requirements. – March 2010

  - Personal Equipment -- Provide a list of equipment

  - Show examples of equipment

- Crew Equipment provided by Troop -- Buy half of the equipment in 2010 and half in 2011.

  - Tents

  - Back packing stoves

- First Aid Training  -- “Philmont requires that a least one person, preferably two, (either an advisor and/or a youth participant) in each crew be currently certified in American Red Cross Wilderness First Aid or the equivalent* and CPR from the American Heart Association, the American Red Cross or the equivalent.”

  - Find the appropriate Red Cross training, register and attend.

  - All adult crew leaders & Any boys who want to attend

- Shakedown Trips – 4 back packing trips to prepare and practice.

  - Leave No Trace (LNT) – learn the aspects of LNT as part of our Philmont training.

- Team building. –  1 team building outing (a fifth outing).

  - October, 2010  - Trip --COPE Team building trip,

  - Design and Make Troop 9 Trek T-Shirts?

### Shakedown Trips

Meals: Dehydrated meals cooked over backpacking stoves.

Water: Carry all needed water for each trip.

Tents: Use back packing tents when needed, otherwise, sleep in shelters.

How:

- Practice using our equipment

  - Packing to reduce weight

  - Packing to carry the weight in the most comfortable manner.

- Find out what works for each person and what does not work

  - Equipment one may have forgotten.

  - Equipment that does not perform

- Practice the skills needed for a successful Philmont Trek.

  - Map and compass reading.

  - Leave No Trace camping.

- Learn how to work together as a team.

- Proposed Shakedown Trips – All trips are leave Friday evening, return Sunday:

  - March, 2010 – Review Equipment

  - April or May 2010 – Shakedown Trip #1 (small overnight hike, 7 miles, as a start).

  - November-- 2010  -- Shakedown Trip #2, about 15 to 20 miles

  - April, 2011 Shakedown Trip #3, about 15 to 20 miles over 2 days

  - May, 2011 -- Shakedown Trip #4, about 15 to 20 miles over 2 days.  Hilly ground, example – Shawnee National Forest

Time Line (Tentative): Philmont 2011 Trek

| Line | Tentative Dates | ## Task or Event |
| --- | --- | --- |
|  | ## Year - 2010 |  |
| 1 | February 12, 2010 | First Payment Due |
| 2 | March, 2010 | Meet with Parents and Boys - Provide personal equipment list - Show examples of personal equipment |
| 3 | April or May, 2010 | Shakedown trip #1, 7 to 10 mile hike, no tents. Example: Kettle Moraine South. |
| 4 | Fall of 2010 | Wilderness First Aid Basic and CPR certification – attendance mandatory for all adults |
| 5 | Fall of 2010 #1 | Trip #2--COPE Team building trip, Milwaukee or Davenport |
| 6 | Fall of 2010 #2 | Shakedown Trip #3, about 15 to 20 miles over 2 days Example: Kettle Moraine North |
| 7 | October 1, 2010 | Second payment due to Philmont |
|  | ## Year – 2011 |  |
| 8 | January 1, 2011 | All youth members age 14 by 1/1/2011 or completed 8th grade be at least 13 by date of attendance. |
| 9 | March 1, 2011 | Final payment due Philmont Receive trek options after final payment is made. |
| 10 | March 1, 2011 | Trek choices mailed (no later than May 1, 2011) |
| 11 | April, 2011 | Shakedown Trip #4, about 15 to 20 miles over 2 days |
| 12 | May, 2011 | Shakedown Trip #5, about 15 to 20 miles over 2 days. Hilly ground, example – Shawnee National Forest. |
| 13 | June 1, 2011 | File National Tour Permit (needed 30 days before) Buy train tickets, Amtrak 800-872-7245 |
| 14 | June 1, 2011 | Philmont Health and medical Records complete with physician and parent/guardian signature |
| 15 | June 1, 2011 | Wilderness First Aid Basic and CPR certification completed with proof of certification. |
| 16 | June 1, 2011 | Trek Itinerary reservation confirmed by Philmont |
| 17 | July 1, 2011 | Arrival Plans and Crew Information Card mailed to Philmont mailed at least 30 days before. |
| 18 | August 11, 2011 | Board Train to Raton, NM, for Philmont, Departs: 3:15 PM |
| 19 | August 12, 2011 | Arrives: 10:56 AM, Aug 11 2010, spend night at Philmont Ranch |
| 20 | August 12-19, 2011 | Arrive at Philmont between 8-11am for Philmont Trek Friday, Aug 12 through Friday, Aug 19, 2011. |
| 21 | August 19, 2011 | Board Train, Departs: 5:32 PM at Raton, NM, for Home |
| 22 | August 20, 2011 | Arrives: 3:20 PM at Union Station, Chicago, IL |

# Crew Equipment & Transportation

| # REI Quarter Dome T2 Tent Item # 761893 $269.00 |  |
| --- | --- |
| # REI Camp Dome 2 Tent Item # 731378 $99.50 |  |

| # MSR DragonFly Backpacking Stove Item # 709002 $129.95 |  |
| --- | --- |
| # MSR Fuel Bottle with CRP Cap - 30 fl. oz. Item # 783963 $19.95 |  |

| ## Transportation #### Between Raton, NM and Union Station, Chicago |  |  |
| --- | --- | --- |
| CHI to RAT | From: Chicago - Union Station, IL (CHI) To: Raton, NM (RAT) Departs: 3:15 PM, Tue Aug 10 2010 Chicago, IL - Union Station (CHI) Arrives: 10:56 AM, Wed Aug 11 2010 Raton, NM (RAT) | Afternoon $121.00 Duration: 20 hr, 41 min |
| RAT to CHI 4 Southwest Chief | Departs: 5:32 PM, Fri Aug 20 2010 Raton, NM (RAT) Station NewsArrives: 3:20 PM, Sat Aug 21 2010 Chicago, IL - Union Station (CHI) Chicago, IL Union Station (CHI) PT20H48M | Afternoon $121.00 Duration: 20 hr, 48 min |
|  |  | Total Cost $242 |